Status Update – Week 4

- FreshBasket (Organic Snacks): Ad spend Rs. 2.5L/month, ROAS 4.2. Client is happy overall but asked for clarity on the daily spend breakdown in the report. I spent 9 hours this week on keyword research, bid adjustments and reporting.

- UrbanPulse (Men’s Grooming): Ad spend Rs. 4L/month, ROAS 2.1 below target. Client is concerned and compared results to their previous agency. I spent 12 hours on restructuring keywords, auditing negatives, competitive analysis and drafting a response. I also noticed their product images are weaker than competitors which may be hurting performance.

- NestWell (Home Fragrances): Ad spend Rs. 1.8L/month, ROAS 3.5 on target. Client also asked about the daily spend breakdown in the report same confusion as FreshBasket. I spent 7 hours on optimization and reporting. Their Flipkart store is active but not advertised which could be a growth opportunity.

Patterns & Recommendations

- Two clients (FreshBasket and NestWell) asked the same question about report columns means report format needs improvement.

- UrbanPulse consumed the most hours but client feels little progress leads to risk of churn unless we make effort more visible.

- NestWell  Flipkart store is unused .

Recommendation: Redesign reporting for clarity, create a tracker to show effort invested and explore Flipkart ads for NestWell.